## Sheet1
PRJ566
| Team Self Selection & Project Selection | Proposal Preparation | Project Overview | Requirements Elicitation: Functional & non-functional | Data & Process Modelling |  |  | Data & Process Modelling, Interface Mockups | Database Design |  | Implementation Planning | PID completion & Presentations
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 |  | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Team Artifacts | Team members information | The Proposed Business Case | PID: introduction, Project Overview | Functional & Nonfunctional Requirements | Business Use Case Diagrams, Activity Diagram, & Use Case Descriptions, DFDs | Business Rules, System Use Case Diagrams, Conceptual Model, Use Case Specifications and corresponding interface mock-ups | Break Week | Interface Mock-ups Domain Class Diagram | Database Design: ERD, Scripts to create, populate, delete tables | Scripts to populate tables (meaningful data) Data Dictionary | Implementation Schedule for PRJ566 - using Microsoft Project Work Breakdown Structure | Measurable deliverables, Acceptance Criteria | Final Presentations PPTs, Completed PID
Team Weekly Deliverables |  |  | Progress Report |  | Progress Report | Team Project Presentations PPTs |  | Progress Report |  | Progress Report |  | Progress Report
Team member Weekly Deliverables |  |  | Action items & tasks report |  | Action items & tasks report |  |  | Action items & tasks report |  | Action items & tasks report |  | Action items & tasks report
All artifacts (team & individual) are to be uploaded to MS teams and are due on Sunday @11:59pm. All artifacts after revision must be included in the PID. Project schedule in MS Project